## Sheet1
Starting Criteria
| Week | 7 | Days
| Weekly Work | 5 | Days
| Weekly Work | 37 | Hours
| Prof Dev Module | 0.25 | Proportion of total year effort
| Live Project | 0.55 | Proportion of Prof Dev
bfbb
| Effort |  |  |  | Totals |  |  | For Selection |  | For Selection |  | For Selection
| Minimum |  |  |  | 5.0875 | Hours per Week |  | Minimum |  | Term |  | Requirements
| Expected | 1 | Extra-curricular hours per night |  | 10.0875 | Hours per Week |  | Expected |  | Non-term |  | Design
| Stretch | 2 | Extra curricular hours per night |  | 15.0875 | Hours per Week |  | Stretch |  |  |  | Impl
None
|  |  | Year | Month | Day
| Start Date |  | 2017 | 10 | 23 | 2017-10-23
|  |  |  | Investigation | [6 empty] | 519.2
|  |  |  | Requirements |  |  | 242.1 | Design |  |  | 277.1 | Implementation | [8 empty] | 770.25 | Release |  |  | 302.1
| Team | Air92
|  |  |  | Term | Term | Term | Term | Term | Term | Term | Term | Non-term | Non-term | Non-term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term |  | Hours
|  | Member | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  |  | Sprint | 1: 0.75; 3: 1.75; 5: 2.75; 7: 3.75; 9: 4.75; 11: 5.75; 13: 6.75; 15: 7.75; 17: 8.75; 19: 9.75; 21: 10.75
|  |  | Commencing | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 |  | Minimum | Expected | Stretch | Total
|  | Abd-Assamad Achouri |  | Expected | Expected | Expected | Expected | Expected | Expected | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch |  | 0 | 60.525 | 241.4 | 301.925
|  | Yusof Bandar |  | Expected | Expected | Expected | Expected | Expected | Expected | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch |  | 0 | 60.525 | 241.4 | 301.925
|  | Evans Mensah Adeenu |  | Expected | Expected | Expected | Expected | Expected | Expected | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch | Stretch |  | 0 | 60.525 | 241.4 | 301.925
|  | Naim Ahmed |  | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected |  | 0 | 221.925 | 0 | 221.925
# |  | Faran Azad |  | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected |  | 0 | 221.925 | 0 | 221.925
|  | Hamza Asif |  | Expected | Expected | Expected | Expected | Expected | Expected | Stretch | Expected | Stretch | Stretch | Stretch | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected |  | 0 | 181.575 | 60.35 | 241.925
|  | Hours | Minimum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Expected | 60.525 | 60.525 | 60.525 | 60.525 | 60.525 | 60.525 | 20.175 | 30.2625 | 20.175 | 20.175 | 20.175 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | Totals | 0 | 807 | 784.55 | 1591.55 | Hours
|  |  | Stretch | 0 | 0 | 0 | 0 | 0 | 0 | 60.35 | 45.2625 | 60.35 | 60.35 | 60.35 | 45.2625 | 45.2625 | 45.2625 | 45.2625 | 45.2625 | 45.2625 | 45.2625 | 45.2625 | 45.2625 | 45.2625 | 45.2625
|  | Total Hours | Week | 60.525 | 60.525 | 60.525 | 60.525 | 60.525 | 60.525 | 80.525 | 75.525 | 80.525 | 80.525 | 80.525 | 75.525 | 75.525 | 75.525 | 75.525 | 75.525 | 75.525 | 75.525 | 75.525 | 75.525 | 75.525 | 75.525 | Total |  |  | 1591.55 |  | Hours
|  | Total Hours | Sprint | 2017-10-30: 121.05; 2017-11-13: 121.05; 2017-11-27: 121.05; 2017-12-11: 156.05; 2017-12-25: 161.05; 2018-01-08: 156.05; 2018-01-22: 151.05; 2018-02-05: 151.05; 2018-02-19: 151.05; 2018-03-05: 151.05; 2018-03-19: 151.05 | Total |  |  | 1591.55 |  | Hours
| You have | 1591.55 | Hours, to spend on your project